## Sheet1
| Description: | Unit: | Assignee: | Left to do: | Tested:
Console | Create project and copy some old code (Linked list, etc..) | - |  | Done | No
| Create a unit for the game content (board state, create move, add soldier, remove soldier, etc..) | BoardManager.c | Tomer / Or | All functions updated. No tests done. | No
| Game Logic (get legal moves, etc..) | GameLogic.c | Or | 1) Tests should be made 2) When are isMatt and isTie called? We should optimize that.. | No
| Minmax improvements | Minimax.c | Tomer | use isTie and isMatt.. | No
| Add a game settings unit | GameSettings.c | Tomer |  | No
| Commands (move, get_moves..) | GameCommands.c | Tomer / Or | 1) Separate commands from parsing commands 2) There's a function called "getScore" - there too we should use isTie and isMatt 3) Support promotion commands for peons | No
| Create a generic GameFlow system (with function pointers) | GameFlow.c (Chess.c) | Tomer | use isTie and isMatt.. | No
| Implement console gui for commands | ConsoleMode.c (Chess.c) | Tomer |  | No
| Implement console gui for drawing the board | ConsoleMode.c (Chess.c) | Tomer |  | No
Intermediate | Implement Save game to XML |  | Tomer |  | No
Gui | Implement a general GUI framework | GuiFW.c | Or |  | Sanity Tests
| Implement window 1.. |  | Or |  | No
| Implement window 2.. |  | Or |  | No
| Implement window 3.. |  | Or |  | No